## Data
Item Key | Summary of Initiatives | Status | Active | Start Date | End Date | Duration | Offset Days | Total Cost | Item Color | Code
SE11-01 | Punchlist Project Proposal | Done | FALSE | 2025-01-01 | 2025-01-08 | 7 | 0 | 0 | Purple | 0
SE11-02 | Initial Site Visit - Architect | Done | FALSE | 2025-01-08 | 2025-01-09 | 1 | 7 | 0 | Dark Blue | 1
SE11-03 | Initial Site Visit - Designer | Done | FALSE | 2025-01-08 | 2025-01-09 | 1 | 7 | 0 | Dark Blue | 1
SE11-04 | Initial Site Visit - GC | Done | FALSE | 2025-01-08 | 2025-01-09 | 1 | 7 | 530.5 | Dark Blue | 1
SE11-05 | Send Architectural RFP | Done | FALSE | 2025-01-09 | 2025-01-10 | 1 | 8 | 0 | Dark Blue | 1
SE11-06 | Architectural Due Diligence & Proposal | Done | FALSE | 2025-01-10 | 2025-01-24 | 14 | 9 | 0 | Light Blue | 2
SE11-07 | Engineering Due Diligence & Proposal | Done | FALSE | 2025-01-10 | 2025-01-24 | 14 | 9 | 0 | Light Blue | 2
SE11-08 | Landscaping Due Diligence & Proposal | Done | FALSE | 2025-01-10 | 2025-01-24 | 14 | 9 | 0 | Light Blue | 2
SE11-09 | Hire Architect / Engineer | Done | FALSE | 2025-01-24 | 2025-02-07 | 14 | 23 | 0 | Light Blue | 2
SE11-10 | Architectual Drafting and Review | Done | FALSE | 2025-02-07 | 2025-03-09 | 30 | 37 | 29400 | Light Blue | 2
SE11-11 | Building Permit Application | Done | FALSE | 2025-03-09 | 2025-03-23 | 14 | 67 | 0 | Light Blue | 2
SE11-12 | Architectural Plan Revisions | Done | FALSE | 2025-03-09 | 2025-03-16 | 7 | 67 | 0 | Light Blue | 2
SE11-13 | Engineering Plan Revisions | Done | FALSE | 2025-03-09 | 2025-03-16 | 7 | 67 | 0 | Light Blue | 2
SE11-14 | Landscaping Plan Revisions | Done | FALSE | 2025-03-09 | 2025-03-16 | 7 | 67 | 0 | Light Blue | 2
SE11-15 | Send Contractor RFP | Done | FALSE | 2025-03-16 | 2025-03-17 | 1 | 74 | 0 | Light Blue | 2
SE11-16 | Planning Board Review - Site / Civil | Done | FALSE | 2025-03-17 | 2025-03-31 | 14 | 75 | 14789.6581 | Grey | 3
SE11-17 | Zoning Board Review | Done | FALSE | 2025-03-17 | 2025-03-31 | 14 | 75 | 7394.829 | Grey | 3
SE11-18 | Architecture Board Review | Done | FALSE | 2025-03-31 | 2025-04-14 | 14 | 89 | 24194.829 | Grey | 3
SE11-19 | Building Department Review | To Do | TRUE | 2025-04-14 | 2025-04-28 | 14 | 103 | 7394.829 | Grey | 3
SE11-20 | Punchlist Value Engineer | To Do | TRUE | 2025-04-14 | 2025-04-28 | 14 | 103 | 0 | Purple | 0
SE11-21 | GC Due Diligence & Proposal | To Do | FALSE | 2025-04-14 | 2025-04-21 | 7 | 103 | 0 | Light Blue | 2
SE11-22 | Design Due Diligence & Proposal | To Do | FALSE | 2025-04-14 | 2025-04-21 | 7 | 103 | 0 | Light Blue | 2
SE11-23 | Review GC Proposals | To Do | FALSE | 2025-04-21 | 2025-04-28 | 7 | 110 | 0 | Light Blue | 2
SE11-24 | Review Design Proposals | To Do | FALSE | 2025-04-21 | 2025-04-28 | 7 | 110 | 0 | Light Blue | 2
SE11-25 | Site Visit (#2) - Contactor | To Do | FALSE | 2025-04-29 | 2025-04-30 | 1 | 118 | 0 | Dark Blue | 1
SE11-26 | Site Visit (#2) - Designer | To Do | FALSE | 2025-04-29 | 2025-04-30 | 1 | 118 | 0 | Dark Blue | 1
SE11-27 | Accept Proposals & Sign Contracts | To Do | FALSE | 2025-04-30 | 2025-05-01 | 1 | 119 | 0 | Dark Blue | 1
SE11-28 | Obtain Building Permits | To Do | FALSE | 2025-05-01 | 2025-05-02 | 1 | 120 | 0 | Grey | 3
SE11-29 | Order Kitchen Appliances | To Do | FALSE | 2025-05-02 | 2025-05-09 | 7 | 121 | 34812.96 | Cyan | 5
SE11-30 | Order Windows & Siding | To Do | FALSE | 2025-05-02 | 2025-05-09 | 7 | 121 | 138972.67 | Cyan | 5
SE11-31 | Order Cabinetry (Kitchen / Bath) | To Do | FALSE | 2025-05-02 | 2025-05-09 | 7 | 121 | 0 | Cyan | 5
SE11-32 | Order Countertops & Tiling | To Do | FALSE | 2025-05-02 | 2025-05-09 | 7 | 121 | 0 | Cyan | 5
SE11-33 | Order Above Grade Flooring | To Do | FALSE | 2025-05-02 | 2025-05-09 | 7 | 121 | 0 | Cyan | 5
SE11-34 | Order Bathroom Vanities | To Do | FALSE | 2025-05-02 | 2025-05-09 | 7 | 121 | 8258.505 | Cyan | 5
SE11-35 | Order Hardware & Fixtures | To Do | FALSE | 2025-05-02 | 2025-05-09 | 7 | 121 | 4726.84 | Cyan | 5
SE11-36 | Order HVAC Unit | To Do | FALSE | 2025-05-02 | 2025-05-09 | 7 | 121 | 922.2 | Cyan | 5
SE11-37 | Shut off of Utilities | To Do | FALSE | 2025-05-09 | 2025-05-10 | 1 | 128 | 0 | Blue | 4
SE11-38 | Demolition of Existing Structure | To Do | FALSE | 2025-05-11 | 2025-05-25 | 14 | 130 | 0 | Blue | 4
SE11-39 | Land Clearing & Site Grading | To Do | FALSE | 2025-05-11 | 2025-06-01 | 21 | 130 | 45738 | Blue | 4
SE11-40 | Excavation for Foundation & Utilities | To Do | FALSE | 2025-06-01 | 2025-06-22 | 21 | 151 | 0 | Blue | 4
SE11-41 | Install OnSite Hospitalities | To Do | FALSE | 2025-06-22 | 2025-06-23 | 1 | 172 | 15605.1 | Blue | 4
SE11-42 | Install Drainage & Stormwater System | To Do | FALSE | 2025-06-22 | 2025-07-06 | 14 | 172 | 0 | Blue | 4
SE11-43 | Form & Pour Foundation Footings | To Do | FALSE | 2025-06-22 | 2025-06-24 | 2 | 172 | 54855 | Blue | 4
SE11-44 | Foundation Inspection #1 | To Do | FALSE | 2025-06-24 | 2025-06-25 | 1 | 174 | 0 | Grey | 3
SE11-45 | Build Foundation Walls / Slab | To Do | FALSE | 2025-06-24 | 2025-07-01 | 7 | 174 | 0 | Blue | 4
SE11-46 | Waterproof Foundation & Backfill | To Do | FALSE | 2025-07-01 | 2025-07-08 | 7 | 181 | 18560 | Blue | 4
SE11-47 | Foundation Utility Tie-In | To Do | FALSE | 2025-07-08 | 2025-07-15 | 7 | 188 | 0 | Blue | 4
SE11-48 | Foundation Inspection #2 | To Do | FALSE | 2025-07-15 | 2025-07-16 | 1 | 195 | 0 | Grey | 3
SE11-49 | Civil Engineering Inspection | To Do | FALSE | 2025-07-16 | 2025-07-17 | 1 | 196 | 0 | Grey | 3
SE11-50 | Frame Floors & Subfloors | To Do | FALSE | 2025-07-16 | 2025-07-23 | 7 | 196 | 11332.2 | Blue | 4
SE11-51 | Frame Exterior & Interior Walls | To Do | FALSE | 2025-07-23 | 2025-07-30 | 7 | 203 | 17671.4 | Blue | 4
SE11-52 | Frame Roof & Install Sheating | To Do | FALSE | 2025-07-30 | 2025-08-06 | 7 | 210 | 5114 | Blue | 4
SE11-53 | Install Windows & Exterior Doors | To Do | FALSE | 2025-08-06 | 2025-08-13 | 7 | 217 | 1161 | Blue | 4
SE11-54 | Framing Inspection | To Do | FALSE | 2025-08-14 | 2025-08-15 | 1 | 225 | 0 | Grey | 3
SE11-55 | Install Roof Shingles | To Do | FALSE | 2025-08-13 | 2025-08-20 | 7 | 224 | 23182 | Blue | 4
SE11-56 | Install Rough Plumbing | To Do | FALSE | 2025-08-20 | 2025-09-03 | 14 | 231 | 10380 | Blue | 4
SE11-57 | Install Rough Electrical | To Do | FALSE | 2025-09-03 | 2025-09-17 | 14 | 245 | 85341.89 | Blue | 4
SE11-58 | Plumbing & Electrical Inspection | To Do | FALSE | 2025-09-17 | 2025-09-18 | 1 | 259 | 0 | Grey | 3
SE11-59 | Install Rough HVAC Ductwork | To Do | FALSE | 2025-09-19 | 2025-10-03 | 14 | 261 | 0 | Blue | 4
SE11-60 | Install Exterior Siding & Insulation | To Do | FALSE | 2025-10-04 | 2025-10-11 | 7 | 276 | 31425 | Blue | 4
SE11-61 | Weatherproof Structure Inspection | To Do | FALSE | 2025-10-12 | 2025-10-13 | 1 | 284 | 0 | Grey | 3
SE11-62 | Install Decks, Patios, & Fences | To Do | FALSE | 2025-10-13 | 2025-10-27 | 14 | 285 | 15270.2 | Blue | 4
SE11-63 | Install Interior Drywall | To Do | FALSE | 2025-10-13 | 2025-10-20 | 7 | 285 | 44853 | Blue | 4
SE11-64 | Install Hardwood / Stone Floors | To Do | FALSE | 2025-10-20 | 2025-10-27 | 7 | 292 | 10612.5 | Blue | 4
SE11-65 | Prime Walls & Ceilings (1st Coat) | To Do | FALSE | 2025-10-27 | 2025-10-29 | 2 | 299 | 48014.1375 | Blue | 4
SE11-66 | Install Interior & Exterior Trim | To Do | FALSE | 2025-10-27 | 2025-11-03 | 7 | 299 | 0 | Blue | 4
SE11-67 | Install Cabinetry (Kitchen & Bath) | To Do | FALSE | 2025-10-27 | 2025-11-03 | 7 | 299 | 0 | Blue | 4
SE11-68 | Install Countertops & Tiling | To Do | FALSE | 2025-10-27 | 2025-11-03 | 7 | 299 | 0 | Blue | 4
SE11-69 | Install Closet Shelving | To Do | FALSE | 2025-10-27 | 2025-11-03 | 7 | 299 | 0 | Blue | 4
SE11-70 | Install Kitchen Appliances | To Do | FALSE | 2025-10-27 | 2025-11-03 | 7 | 299 | 0 | Blue | 4
SE11-71 | Install Interior Hardware | To Do | FALSE | 2025-10-27 | 2025-11-03 | 7 | 299 | 0 | Blue | 4
SE11-72 | Install Plumbing Fixtures | To Do | FALSE | 2025-10-27 | 2025-11-03 | 7 | 299 | 50763.1 | Blue | 4
SE11-73 | Install Electrical Fixtures | To Do | FALSE | 2025-10-27 | 2025-11-03 | 7 | 299 | 17750.8 | Blue | 4
SE11-74 | Install HVAC Units & Thermostats | To Do | FALSE | 2025-10-27 | 2025-11-03 | 7 | 299 | 9237.5 | Blue | 4
SE11-75 | Paint Walls & Ceilings (2nd Coat) | To Do | FALSE | 2025-11-03 | 2025-11-17 | 14 | 306 | 0 | Blue | 4
SE11-76 | Stain Hardwood Floors (1st Coat) | To Do | FALSE | 2025-11-17 | 2025-11-19 | 2 | 320 | 97.8 | Blue | 4
SE11-77 | Stain Hardwood Floors (2nd Coat) | To Do | FALSE | 2025-11-19 | 2025-11-21 | 2 | 322 | 5651 | Blue | 4
SE11-78 | Install Flooring (Carpet & LVF) | To Do | FALSE | 2025-11-19 | 2025-11-21 | 2 | 322 | 1436 | Blue | 4
SE11-79 | Order Exterior Landscaping | To Do | FALSE | 2025-11-21 | 2025-11-22 | 1 | 324 | 4716 | Cyan | 5
SE11-80 | Pour Driveway & Walkways | To Do | FALSE | 2025-11-22 | 2025-11-24 | 2 | 325 | 132875.5601 | Blue | 4
SE11-81 | Install Exterior Landscaping | To Do | FALSE | 2025-11-22 | 2025-11-29 | 7 | 325 | 0 | Blue | 4
SE11-82 | Final Site Survey | To Do | FALSE | 2025-11-22 | 2025-11-23 | 1 | 325 | 0 | Blue | 4
SE11-83 | Deck and Patio Inspection | To Do | FALSE | 2025-11-29 | 2025-11-30 | 1 | 332 | 276.05 | Grey | 3
SE11-84 | Interior & Exterior Touch-ups | To Do | FALSE | 2025-11-30 | 2025-12-02 | 2 | 333 | 0 | Blue | 4
SE11-85 | C of O Final Inspection | To Do | FALSE | 2025-12-02 | 2025-12-03 | 1 | 335 | 0 | Grey | 3
SE11-86 | Obtain Certificate of Occupancy | To Do | FALSE | 2025-12-03 | 2025-12-04 | 1 | 336 | 0 | Grey | 3
SE11-87 | Moving Services (1 Week) | To Do | FALSE | 2025-12-04 | 2025-12-05 | 1 | 337 | 0 | Blue | 4
SE11-88 | Final Touch-ups & Repairs | To Do | FALSE | 2025-12-05 | 2025-12-07 | 2 | 338 | 0 | Blue | 4
SE11-89 | Cleanup & Debris Removal | To Do | FALSE | 2025-12-07 | 2025-12-09 | 2 | 340 | 0 | Blue | 4
SE11-90 | Final Punchlist Walk-Through | To Do | FALSE | 2025-12-09 | 2025-12-10 | 1 | 342 | 0 | Purple | 0
Formulas:
End Date = [Start Date]+[Duration]
Start Date = [End Date, row above]
Start Date = [Start Date, row above]

## Pricing
`
11 Clinton Lane - Project Information
Current Date: | 2025-03-22 |  |  |  | Total Project Duation (Hrs) |  | 2183.264
Project Start: | 2025-01-01 |  |  |  | Expected Completion Date |  | 2025-12-10
Lot Size | 43560 |  |  |  | Construction Cost |  | 933317.0578 |  | Builder Grade (%) | 75%
Building SF | 4000 |  |  |  | GC Fee (%) | 20% | 186663.4116 |  | Market Grade (%) | 85%
# of Stories | 2 |  |  |  | Punchlist Fee (%) | 5% | 46665.8529 |  | Punchlist Grade (%) | 100%
Above Grade SF | 3400 |  |  |  | Total Project Cost |  | 1166646.3222 |  | Design Grade (%) | 115%
Below Grade SF | 600 |  |  |  | $ per SF Cost |  | 291.6616 |  | Luxuary Grade (%) | 125%
Unit / Service Desciption | Unit Cost (1) | % Market Grade | Unit Cost + Grade | Total Units / SF | Labor Rate (Hr) | Expected Hours | Labor + Materials | Waste (10.00%) | Total Item Cost | Initiative Key
Aluminum Sheathing | 10 | 100% | 10 | 400 | 85 | 4 | 340 | 434 | 5114 | SE11-52
Appliances (36" Range) | 5759.2 | 100% | 5759.2 | 1 | 100 | 2 | 200 | 595.92 | 6755.12 | SE11-29
Appliances (48” Range) | 9279.2 | 100% | 9279.2 | 0 | 100 | 0 | 0 | 0 | 0 | SE11-29
Appliances (60" Range) | 12799.2 | 100% | 12799.2 | 0 | 100 | 0 | 0 | 0 | 0 | SE11-29
Appliances (Dishwasher) | 1119.2 | 100% | 1119.2 | 1 | 100 | 2 | 200 | 131.92 | 1651.12 | SE11-29
Appliances (30" Oven) | 3759.2 | 100% | 3759.2 | 1 | 100 | 2 | 200 | 395.92 | 4555.12 | SE11-29
Appliances (30" Oven x2) | 5919.2 | 100% | 5919.2 | 0 | 100 | 0 | 0 | 0 | 0 | SE11-29
Appliances (Microwave) | 919.2 | 100% | 919.2 | 1 | 100 | 2 | 200 | 111.92 | 1431.12 | SE11-29
Appliances (Range, Electic) | 2399.2 | 100% | 2399.2 | 1 | 100 | 2 | 200 | 259.92 | 3059.12 | SE11-29
Appliances (Range, Gas) | 1919.2 | 100% | 1919.2 | 0 | 100 | 0 | 0 | 0 | 0 | SE11-29
Appliances (Range, Induction) | 3199.2 | 100% | 3199.2 | 0 | 100 | 0 | 0 | 0 | 0 | SE11-29
Appliances (Freezer) | 6799.2 | 100% | 6799.2 | 1 | 100 | 2 | 200 | 699.92 | 7899.12 | SE11-29
Appliances (Fridge) | 6799.2 | 100% | 6799.2 | 1 | 100 | 2 | 200 | 699.92 | 7899.12 | SE11-29
Appliances (Fridge / Freezer) | 12799.2 | 100% | 12799.2 | 0 | 100 | 0 | 0 | 0 | 0 | SE11-29
Appliances (Fridge / Mini) | 1039.2 | 100% | 1039.2 | 1 | 100 | 2 | 200 | 123.92 | 1563.12 | SE11-29
Appliances (Warming Drawer) | 1439.2 | 100% | 1439.2 | 0 | 100 | 0 | 0 | 0 | 0 | SE11-29
Approvals (Landscaping) | 6722.5718 | 100% | 6722.5718 | 1 | 0 | 30 | 0 | 672.2572 | 7394.829 | SE11-16
Approvals (Architectual) | 6722.5718 | 100% | 6722.5718 | 1 | 0 | 30 | 0 | 672.2572 | 7394.829 | SE11-18
Approvals (Engineering) | 6722.5718 | 100% | 6722.5718 | 1 | 0 | 30 | 0 | 672.2572 | 7394.829 | SE11-19
Approvals (Zoning) | 6722.5718 | 100% | 6722.5718 | 1 | 0 | 30 | 0 | 672.2572 | 7394.829 | SE11-16
Approvals (Site-Plan) | 6722.5718 | 100% | 6722.5718 | 1 | 0 | 30 | 0 | 672.2572 | 7394.829 | SE11-17
Cabinetry (Kitchen) | 1200 | 100% | 1200 | 30 | 100 | 6 | 600 | 3660 | 40860 | SE11-30
Copper (Gutters) | 17.5 | 100% | 17.5 | 400 | 87.5 | 20 | 1750 | 875 | 11375 | SE11-60
Copper (Wiring) | 6 | 100% | 6 | 10000 | 90 | 100 | 9000 | 6900 | 84900 | SE11-57
Deck (Hardwood) | 25 | 100% | 25 | 1 | 80 | 1 | 80 | 10.5 | 195.5 | SE11-62
Deck (Vinyl) | 18 | 100% | 18 | 0 | 65 | 0 | 0 | 0 | 0 | SE11-62
Driveway (Asphault) | 6 | 100% | 6 | 600 | 60 | 6 | 360 | 396 | 4716 | SE11-79
Driveway (Crushed Gravel) | 3 | 100% | 3 | 0 | 45 | 0 | 0 | 0 | 0 | SE11-79
Driveway (Pavers) | 12 | 100% | 12 | 0 | 75 | 0 | 0 | 0 | 0 | SE11-79
Electrical (Circuit Breaker) | 400 | 100% | 400 | 1 | 90 | 0.01 | 0.9 | 40.09 | 441.89 | SE11-57
Electrical (Generator) | 5000 | 100% | 5000 | 1 | 100 | 0.01 | 1 | 500.1 | 5502.1 | SE11-72
Flooring (Carpet) | 4 | 100% | 4 | 0 | 55 | 0 | 0 | 0 | 0 | SE11-77
Flooring (Hardwood) | 8 | 100% | 8 | 3400 | 65 | 68 | 4420 | 3162 | 39202 | SE11-63
Flooring (LVF) | 6 | 100% | 6 | 0 | 50 | 0 | 0 | 0 | 0 | SE11-77
Flooring (Wood Stain) | 1 | 100% | 1 | 3400 | 65 | 14 | 910 | 431 | 5651 | SE11-63
Flooring (Wood Stain #2) | 1 | 100% | 1 | 3400 | 65 | 14 | 910 | 431 | 5651 | SE11-77
Flooring (Stone) | 15 | 100% | 15 | 0 | 75 | 0 | 0 | 0 | 0 | SE11-75
Flooring (Vinyl) | 3 | 100% | 3 | 1 | 45 | 1 | 45 | 4.8 | 97.8 | SE11-76
Foundations (Concrete) | 12 | 100% | 12 | 3000 | 70 | 30 | 2100 | 3810 | 44010 | SE11-43
Foundations (Steel) | 15 | 100% | 15 | 600 | 75 | 6 | 450 | 945 | 10845 | SE11-43
Hardware (Blinds) | 6 | 100% | 6 | 6 | 40 | 0.06 | 2.4 | 3.84 | 44.64 | SE11-35
Hardware (Door Knobs) | 20 | 100% | 20 | 20 | 50 | 0.2 | 10 | 41 | 461 | SE11-35
Hardware (Doors) | 150 | 100% | 150 | 20 | 65 | 4 | 260 | 326 | 3846 | SE11-35
Hardware (Shades) | 8 | 100% | 8 | 14 | 40 | 3 | 120 | 23.2 | 375.2 | SE11-35
Hardware (Windows) | 600 | 100% | 600 | 40 | 60 | 14 | 840 | 2484 | 28164 | SE11-30
HVAC (Central AC) | 6 | 100% | 6 | 40 | 75 | 0.4 | 30 | 27 | 327 | SE11-36
HVAC (Heated Floors) | 12 | 100% | 12 | 40 | 80 | 0.4 | 32 | 51.2 | 595.2 | SE11-36
HVAC (Split System) | 8 | 100% | 8 | 40 | 70 | 0.4 | 28 | 34.8 | 410.8 | SE11-73
HVAC (Duct Wok) | 15 | 100% | 15 | 1000 | 40 | 10 | 400 | 1540 | 17340 | SE11-73
Insulation (Foam) | 2.5 | 100% | 2.5 | 5000 | 60 | 50 | 3000 | 1550 | 20050 | SE11-60
Insulation (Fiber Glass) | 1.5 | 100% | 1.5 | 0 | 40 | 0 | 0 | 0 | 0 | SE11-60
Labor (Architect) | 0 | 100% | 0 | 1 | 350 | 40 | 14000 | 1400 | 29400 | SE11-10
Labor (Designer) | 0 | 100% | 0 | 1 | 100 | 80 | 8000 | 800 | 16800 | SE11-18
Labor (GC) | 0 | 100% | 0 | 1 | 0 | 40 | 0 | 0 | 0 | SE11-17
Landscaping (Dirt) | 0 | 100% | 0 | 43560 | 50 | 435.6 | 21780 | 2178 | 45738 | SE11-39
Landscaping (Grass Seed) | 0 | 100% | 0 | 43560 | 50 | 435.6 | 21780 | 2178 | 45738 | SE11-80
Landscaping (Grass Sod) | 0 | 100% | 0 | 0 | 50 | 0 | 0 | 0 | 0 | SE11-80
Landscaping (Mailbox) | 250 | 100% | 250 | 1 | 50 | 0.01 | 0.5 | 25.05 | 276.05 | SE11-83
Landscaping (Rock) | 100 | 100% | 100 | 0 | 50 | 0 | 0 | 0 | 0 | SE11-39
Landscaping (Shade Trees) | 1000 | 100% | 1000 | 76.23 | 50 | 0.7623 | 38.115 | 7626.8115 | 83933.0415 | SE11-80
Landscaping (Shrubs) | 50 | 100% | 50 | 57.1725 | 50 | 0.57173 | 28.5863 | 288.7211 | 3204.5186 | SE11-80
Light Switches | 30 | 100% | 30 | 54 | 50 | 3 | 150 | 177 | 2097 | SE11-72
Lighting Fixtures | 150 | 100% | 150 | 16 | 70 | 2 | 140 | 254 | 2934 | SE11-72
Municipal Inspection | 0 | 100% | 0 | 1 | 0 | 2 | 0 | 0 | 0 | SE11-83
Paint (2nd Coat) | 1.5 | 100% | 1.5 | 5000 | 45 | 25 | 1125 | 862.5 | 10612.5 | SE11-64
Paint (1st Coat / Primer) | 1.25 | 100% | 1.25 | 5000 | 45 | 25 | 1125 | 737.5 | 9237.5 | SE11-74
Patio (Blue Stone) | 30 | 100% | 30 | 436 | 75 | 4.36 | 327 | 1340.7 | 15074.7 | SE11-62
Patio (Brick) | 18 | 100% | 18 | 0 | 50 | 0 | 0 | 0 | 0 | SE11-62
Patio (Gravel) | 22 | 100% | 22 | 0 | 60 | 0 | 0 | 0 | 0 | SE11-62
Plywood / Subboard | 1.8 | 100% | 1.8 | 3740 | 50 | 37.4 | 1870 | 860.2 | 11332.2 | SE11-50
PVC Pipes | 1.5 | 100% | 1.5 | 4000 | 45 | 40 | 1800 | 780 | 10380 | SE11-56
Recessed Lighting | 90 | 100% | 90 | 400 | 75 | 4 | 300 | 3630 | 40230 | SE11-72
Sealant (Caulking) | 0.75 | 100% | 0.75 | 1000 | 40 | 4 | 160 | 91 | 1161 | SE11-53
Site Visit (Architect) | 0 | 100% | 0 | 1 | 0 | 16 | 0 | 0 | 0 | SE11-63
Site Visit (Contractor) | 0 | 100% | 0 | 1 | 0 | 16 | 0 | 0 | 0 | SE11-55
Site Visit (Designer) | 0 | 100% | 0 | 1 | 0 | 8 | 0 | 0 | 0 | SE11-55
Site Vist (Punchlist) | 0 | 100% | 0 | 1 | 0 | 6 | 0 | 0 | 0 | SE11-55
Sheetrock | 1.25 | 100% | 1.25 | 4400 | 55 | 44 | 2420 | 792 | 11132 | SE11-55
Shelving (Closets) | 10 | 100% | 10 | 1000 | 50 | 10 | 500 | 1050 | 12050 | SE11-55
Shingels (Asphalt) | 4 | 100% | 4 | 12800 | 50 | 128 | 6400 | 5760 | 69760 | SE11-30
Shinges (Metal) | 10 | 100% | 10 | 0 | 75 | 0 | 0 | 0 | 0 | SE11-30
Shinges (Slate) | 20 | 100% | 20 | 0 | 90 | 0 | 0 | 0 | 0 | SE11-30
Shingles (Wood) | 12 | 100% | 12 | 1 | 70 | 0.01 | 0.7 | 1.27 | 14.67 | SE11-30
Siding (Brick) | 15 | 100% | 15 | 1 | 75 | 1 | 75 | 9 | 174 | SE11-30
Siding (Hardie Board) | 9 | 100% | 9 | 0 | 60 | 0 | 0 | 0 | 0 | SE11-02
Siding (Shutters) | 2.5 | 100% | 2.5 | 0 | 50 | 0 | 0 | 0 | 0 | SE11-03
Siding (Stone) | 20 | 100% | 20 | 16 | 85 | 1 | 85 | 40.5 | 530.5 | SE11-04
Siding (Wood) | 10 | 100% | 10 | 0 | 65 | 0 | 0 | 0 | 0 | SE11-01
Support Beams (Steel) | 400 | 100% | 400 | 40 | 85 | 0.4 | 34 | 1603.4 | 17671.4 | SE11-51
Support Beams (Wood) | 10 | 100% | 10 | 0 | 70 | 0 | 0 | 0 | 0 | SE11-51
Trim (Baseboard Molding) | 3 | 100% | 3 | 2667 | 60 | 54 | 3240 | 1124.1 | 15605.1 | SE11-41
Trim (Crown Molding) | 4 | 100% | 4 | 2667 | 70 | 54 | 3780 | 1444.8 | 19672.8 | SE11-65
Trim (Exterior) | 6 | 100% | 6 | 2667 | 75 | 54 | 4050 | 2005.2 | 26107.2 | SE11-65
Trim (Finshes) | 2.5 | 100% | 2.5 | 400.05 | 60 | 9 | 540 | 154.0125 | 2234.1375 | SE11-65
Temporary Utilities | 500 | 100% | 500 | 2 | 40 | 4 | 160 | 116 | 1436 | SE11-78
Tyveck / Waterproofing | 1.25 | 100% | 1.25 | 8000 | 45 | 80 | 3600 | 1360 | 18560 | SE11-46
Vanity (Bathtub) | 1200 | 100% | 1200 | 1 | 60 | 0.01 | 0.6 | 120.06 | 1321.26 | SE11-34
Vanity (Bathtub/Shower) | 1500 | 100% | 1500 | 1 | 70 | 0.01 | 0.7 | 150.07 | 1651.47 | SE11-34
Vanity (Bidet) | 600 | 100% | 600 | 1 | 60 | 0.01 | 0.6 | 60.06 | 661.26 | SE11-34
Vanity (Double Sink) | 1800 | 100% | 1800 | 1 | 65 | 0.01 | 0.65 | 180.065 | 1981.365 | SE11-34
Vanity (Shower) | 5000 | 100% | 5000 | 0 | 60 | 0 | 0 | 0 | 0 | SE11-34
Vanity (Sink) | 800 | 100% | 800 | 3 | 50 | 0.03 | 1.5 | 240.15 | 2643.15 | SE11-34
933317.0578

## Pricing (2)
`
11 Clinton Lane - Project Information
Current Date: | 2025-03-22 |  |  |  | Total Project Duation (Hrs) |  | 2183.264
Project Start: | 2025-01-01 |  |  |  | Expected Completion Date |  | 2025-12-10
Lot Size | 43560 |  |  |  | Construction Cost |  | 933317.0578 |  | Builder Grade (%) | 75%
Building SF | 4000 |  |  |  | GC Fee (%) | 20% | 186663.4116 |  | Market Grade (%) | 85%
# of Stories | 2 |  |  |  | Punchlist Fee (%) | 5% | 46665.8529 |  | Punchlist Grade (%) | 100%
Above Grade SF | 3400 |  |  |  | Total Project Cost |  | 1166646.3222 |  | Design Grade (%) | 115%
Below Grade SF | 600 |  |  |  | $ per SF Cost |  | 291.6616 |  | Luxuary Grade (%) | 125%
Unit / Service Desciption | Unit Cost (1) | % Market Grade | Unit Cost + Grade | Total Units / SF | Labor Rate (Hr) | Expected Hours | Instillation Cost | Waste (10.00%) | Total Item Cost | Initiative Key
Aluminum Sheathing | 10 | 100% | 10 | 400 | 85 | 4 | 340 | 434 | 5114 | SE11-52
Appliances (36" Range) | 5759.2 | 100% | 5759.2 | 1 | 100 | 2 | 200 | 595.92 | 6755.12 | SE11-29
Appliances (48” Range) | 9279.2 | 100% | 9279.2 | 0 | 100 | 0 | 0 | 0 | 0 | SE11-29
Appliances (60" Range) | 12799.2 | 100% | 12799.2 | 0 | 100 | 0 | 0 | 0 | 0 | SE11-29
Appliances (Dishwasher) | 1119.2 | 100% | 1119.2 | 1 | 100 | 2 | 200 | 131.92 | 1651.12 | SE11-29
Appliances (30" Oven) | 3759.2 | 100% | 3759.2 | 1 | 100 | 2 | 200 | 395.92 | 4555.12 | SE11-29
Appliances (30" Oven x2) | 5919.2 | 100% | 5919.2 | 0 | 100 | 0 | 0 | 0 | 0 | SE11-29
Appliances (Microwave) | 919.2 | 100% | 919.2 | 1 | 100 | 2 | 200 | 111.92 | 1431.12 | SE11-29
Appliances (Range, Electic) | 2399.2 | 100% | 2399.2 | 1 | 100 | 2 | 200 | 259.92 | 3059.12 | SE11-29
Appliances (Range, Gas) | 1919.2 | 100% | 1919.2 | 0 | 100 | 0 | 0 | 0 | 0 | SE11-29
Appliances (Range, Induction) | 3199.2 | 100% | 3199.2 | 0 | 100 | 0 | 0 | 0 | 0 | SE11-29
Appliances (Freezer) | 6799.2 | 100% | 6799.2 | 1 | 100 | 2 | 200 | 699.92 | 7899.12 | SE11-29
Appliances (Fridge) | 6799.2 | 100% | 6799.2 | 1 | 100 | 2 | 200 | 699.92 | 7899.12 | SE11-29
Appliances (Fridge / Freezer) | 12799.2 | 100% | 12799.2 | 0 | 100 | 0 | 0 | 0 | 0 | SE11-29
Appliances (Fridge / Mini) | 1039.2 | 100% | 1039.2 | 1 | 100 | 2 | 200 | 123.92 | 1563.12 | SE11-29
Appliances (Warming Drawer) | 1439.2 | 100% | 1439.2 | 0 | 100 | 0 | 0 | 0 | 0 | SE11-29
Approvals (Landscaping) | 6722.5718 | 100% | 6722.5718 | 1 | 0 | 30 | 0 | 672.2572 | 7394.829 | SE11-16
Approvals (Architectual) | 6722.5718 | 100% | 6722.5718 | 1 | 0 | 30 | 0 | 672.2572 | 7394.829 | SE11-18
Approvals (Engineering) | 6722.5718 | 100% | 6722.5718 | 1 | 0 | 30 | 0 | 672.2572 | 7394.829 | SE11-19
Approvals (Zoning) | 6722.5718 | 100% | 6722.5718 | 1 | 0 | 30 | 0 | 672.2572 | 7394.829 | SE11-16
Approvals (Site-Plan) | 6722.5718 | 100% | 6722.5718 | 1 | 0 | 30 | 0 | 672.2572 | 7394.829 | SE11-17
Cabinetry (Kitchen) | 1200 | 100% | 1200 | 30 | 100 | 6 | 600 | 3660 | 40860 | SE11-30
Copper (Gutters) | 17.5 | 100% | 17.5 | 400 | 87.5 | 20 | 1750 | 875 | 11375 | SE11-60
Copper (Wiring) | 6 | 100% | 6 | 10000 | 90 | 100 | 9000 | 6900 | 84900 | SE11-57
Deck (Hardwood) | 25 | 100% | 25 | 1 | 80 | 1 | 80 | 10.5 | 195.5 | SE11-62
Deck (Vinyl) | 18 | 100% | 18 | 0 | 65 | 0 | 0 | 0 | 0 | SE11-62
Driveway (Asphault) | 6 | 100% | 6 | 600 | 60 | 6 | 360 | 396 | 4716 | SE11-79
Driveway (Crushed Gravel) | 3 | 100% | 3 | 0 | 45 | 0 | 0 | 0 | 0 | SE11-79
Driveway (Pavers) | 12 | 100% | 12 | 0 | 75 | 0 | 0 | 0 | 0 | SE11-79
Electrical (Circuit Breaker) | 400 | 100% | 400 | 1 | 90 | 0.01 | 0.9 | 40.09 | 441.89 | SE11-57
Electrical (Generator) | 5000 | 100% | 5000 | 1 | 100 | 0.01 | 1 | 500.1 | 5502.1 | SE11-72
Flooring (Carpet) | 4 | 100% | 4 | 0 | 55 | 0 | 0 | 0 | 0 | SE11-77
Flooring (Hardwood) | 8 | 100% | 8 | 3400 | 65 | 68 | 4420 | 3162 | 39202 | SE11-63
Flooring (LVF) | 6 | 100% | 6 | 0 | 50 | 0 | 0 | 0 | 0 | SE11-77
Flooring (Wood Stain) | 1 | 100% | 1 | 3400 | 65 | 14 | 910 | 431 | 5651 | SE11-63
Flooring (Wood Stain #2) | 1 | 100% | 1 | 3400 | 65 | 14 | 910 | 431 | 5651 | SE11-77
Flooring (Stone) | 15 | 100% | 15 | 0 | 75 | 0 | 0 | 0 | 0 | SE11-75
Flooring (Vinyl) | 3 | 100% | 3 | 1 | 45 | 1 | 45 | 4.8 | 97.8 | SE11-76
Foundations (Concrete) | 12 | 100% | 12 | 3000 | 70 | 30 | 2100 | 3810 | 44010 | SE11-43
Foundations (Steel) | 15 | 100% | 15 | 600 | 75 | 6 | 450 | 945 | 10845 | SE11-43
Hardware (Blinds) | 6 | 100% | 6 | 6 | 40 | 0.06 | 2.4 | 3.84 | 44.64 | SE11-35
Hardware (Door Knobs) | 20 | 100% | 20 | 20 | 50 | 0.2 | 10 | 41 | 461 | SE11-35
Hardware (Doors) | 150 | 100% | 150 | 20 | 65 | 4 | 260 | 326 | 3846 | SE11-35
Hardware (Shades) | 8 | 100% | 8 | 14 | 40 | 3 | 120 | 23.2 | 375.2 | SE11-35
Hardware (Windows) | 600 | 100% | 600 | 40 | 60 | 14 | 840 | 2484 | 28164 | SE11-30
HVAC (Central AC) | 6 | 100% | 6 | 40 | 75 | 0.4 | 30 | 27 | 327 | SE11-36
HVAC (Heated Floors) | 12 | 100% | 12 | 40 | 80 | 0.4 | 32 | 51.2 | 595.2 | SE11-36
HVAC (Split System) | 8 | 100% | 8 | 40 | 70 | 0.4 | 28 | 34.8 | 410.8 | SE11-73
HVAC (Duct Wok) | 15 | 100% | 15 | 1000 | 40 | 10 | 400 | 1540 | 17340 | SE11-73
Insulation (Foam) | 2.5 | 100% | 2.5 | 5000 | 60 | 50 | 3000 | 1550 | 20050 | SE11-60
Insulation (Fiber Glass) | 1.5 | 100% | 1.5 | 0 | 40 | 0 | 0 | 0 | 0 | SE11-60
Labor (Architect) | 0 | 100% | 0 | 1 | 350 | 40 | 14000 | 1400 | 29400 | SE11-10
Labor (Designer) | 0 | 100% | 0 | 1 | 100 | 80 | 8000 | 800 | 16800 | SE11-18
Labor (GC) | 0 | 100% | 0 | 1 | 0 | 40 | 0 | 0 | 0 | SE11-17
Landscaping (Dirt) | 0 | 100% | 0 | 43560 | 50 | 435.6 | 21780 | 2178 | 45738 | SE11-39
Landscaping (Grass Seed) | 0 | 100% | 0 | 43560 | 50 | 435.6 | 21780 | 2178 | 45738 | SE11-80
Landscaping (Grass Sod) | 0 | 100% | 0 | 0 | 50 | 0 | 0 | 0 | 0 | SE11-80
Landscaping (Mailbox) | 250 | 100% | 250 | 1 | 50 | 0.01 | 0.5 | 25.05 | 276.05 | SE11-83
Landscaping (Rock) | 100 | 100% | 100 | 0 | 50 | 0 | 0 | 0 | 0 | SE11-39
Landscaping (Shade Trees) | 1000 | 100% | 1000 | 76.23 | 50 | 0.7623 | 38.115 | 7626.8115 | 83933.0415 | SE11-80
Landscaping (Shrubs) | 50 | 100% | 50 | 57.1725 | 50 | 0.57173 | 28.5863 | 288.7211 | 3204.5186 | SE11-80
Light Switches | 30 | 100% | 30 | 54 | 50 | 3 | 150 | 177 | 2097 | SE11-72
Lighting Fixtures | 150 | 100% | 150 | 16 | 70 | 2 | 140 | 254 | 2934 | SE11-72
Municipal Inspection | 0 | 100% | 0 | 1 | 0 | 2 | 0 | 0 | 0 | SE11-83
Paint (2nd Coat) | 1.5 | 100% | 1.5 | 5000 | 45 | 25 | 1125 | 862.5 | 10612.5 | SE11-64
Paint (1st Coat / Primer) | 1.25 | 100% | 1.25 | 5000 | 45 | 25 | 1125 | 737.5 | 9237.5 | SE11-74
Patio (Blue Stone) | 30 | 100% | 30 | 436 | 75 | 4.36 | 327 | 1340.7 | 15074.7 | SE11-62
Patio (Brick) | 18 | 100% | 18 | 0 | 50 | 0 | 0 | 0 | 0 | SE11-62
Patio (Gravel) | 22 | 100% | 22 | 0 | 60 | 0 | 0 | 0 | 0 | SE11-62
Plywood / Subboard | 1.8 | 100% | 1.8 | 3740 | 50 | 37.4 | 1870 | 860.2 | 11332.2 | SE11-50
PVC Pipes | 1.5 | 100% | 1.5 | 4000 | 45 | 40 | 1800 | 780 | 10380 | SE11-56
Recessed Lighting | 90 | 100% | 90 | 400 | 75 | 4 | 300 | 3630 | 40230 | SE11-72
Sealant (Caulking) | 0.75 | 100% | 0.75 | 1000 | 40 | 4 | 160 | 91 | 1161 | SE11-53
Site Visit (Architect) | 0 | 100% | 0 | 1 | 0 | 16 | 0 | 0 | 0 | SE11-63
Site Visit (Contractor) | 0 | 100% | 0 | 1 | 0 | 16 | 0 | 0 | 0 | SE11-55
Site Visit (Designer) | 0 | 100% | 0 | 1 | 0 | 8 | 0 | 0 | 0 | SE11-55
Site Vist (Punchlist) | 0 | 100% | 0 | 1 | 0 | 6 | 0 | 0 | 0 | SE11-55
Sheetrock | 1.25 | 100% | 1.25 | 4400 | 55 | 44 | 2420 | 792 | 11132 | SE11-55
Shelving (Closets) | 10 | 100% | 10 | 1000 | 50 | 10 | 500 | 1050 | 12050 | SE11-55
Shingels (Asphalt) | 4 | 100% | 4 | 12800 | 50 | 128 | 6400 | 5760 | 69760 | SE11-30
Shinges (Metal) | 10 | 100% | 10 | 0 | 75 | 0 | 0 | 0 | 0 | SE11-30
Shinges (Slate) | 20 | 100% | 20 | 0 | 90 | 0 | 0 | 0 | 0 | SE11-30
Shingles (Wood) | 12 | 100% | 12 | 1 | 70 | 0.01 | 0.7 | 1.27 | 14.67 | SE11-30
Siding (Brick) | 15 | 100% | 15 | 1 | 75 | 1 | 75 | 9 | 174 | SE11-30
Siding (Hardie Board) | 9 | 100% | 9 | 0 | 60 | 0 | 0 | 0 | 0 | SE11-02
Siding (Shutters) | 2.5 | 100% | 2.5 | 0 | 50 | 0 | 0 | 0 | 0 | SE11-03
Siding (Stone) | 20 | 100% | 20 | 16 | 85 | 1 | 85 | 40.5 | 530.5 | SE11-04
Siding (Wood) | 10 | 100% | 10 | 0 | 65 | 0 | 0 | 0 | 0 | SE11-01
Support Beams (Steel) | 400 | 100% | 400 | 40 | 85 | 0.4 | 34 | 1603.4 | 17671.4 | SE11-51
Support Beams (Wood) | 10 | 100% | 10 | 0 | 70 | 0 | 0 | 0 | 0 | SE11-51
Trim (Baseboard Molding) | 3 | 100% | 3 | 2667 | 60 | 54 | 3240 | 1124.1 | 15605.1 | SE11-41
Trim (Crown Molding) | 4 | 100% | 4 | 2667 | 70 | 54 | 3780 | 1444.8 | 19672.8 | SE11-65
Trim (Exterior) | 6 | 100% | 6 | 2667 | 75 | 54 | 4050 | 2005.2 | 26107.2 | SE11-65
Trim (Finshes) | 2.5 | 100% | 2.5 | 400.05 | 60 | 9 | 540 | 154.0125 | 2234.1375 | SE11-65
Temporary Utilities | 500 | 100% | 500 | 2 | 40 | 4 | 160 | 116 | 1436 | SE11-78
Tyveck / Waterproofing | 1.25 | 100% | 1.25 | 8000 | 45 | 80 | 3600 | 1360 | 18560 | SE11-46
Vanity (Bathtub) | 1200 | 100% | 1200 | 1 | 60 | 0.01 | 0.6 | 120.06 | 1321.26 | SE11-34
Vanity (Bathtub/Shower) | 1500 | 100% | 1500 | 1 | 70 | 0.01 | 0.7 | 150.07 | 1651.47 | SE11-34
Vanity (Bidet) | 600 | 100% | 600 | 1 | 60 | 0.01 | 0.6 | 60.06 | 661.26 | SE11-34
Vanity (Double Sink) | 1800 | 100% | 1800 | 1 | 65 | 0.01 | 0.65 | 180.065 | 1981.365 | SE11-34
Vanity (Shower) | 5000 | 100% | 5000 | 0 | 60 | 0 | 0 | 0 | 0 | SE11-34
Vanity (Sink) | 800 | 100% | 800 | 3 | 50 | 0.03 | 1.5 | 240.15 | 2643.15 | SE11-34
933317.0578

## Color Code
Code | Color
0 | Purple
1 | Dark Blue
2 | Light Blue
3 | Grey
4 | Blue
5 | Cyan