## Data
Item Key | Summary of Initiatives | Status | Active | Start Date | End Date | Duration | Offset Days | Total Cost | Item Color | Code
SE11-01 | Punchlist Project Proposal | Done | FALSE | 2025-01-01 | 2025-01-08 | 7 | 0 | 5500 | Purple | 0
SE11-02 | Initial Project Survey | Done | FALSE | 2025-01-08 | 2025-01-15 | 7 | 7 | 1100 | Dark Blue | 1
SE11-03 | Initial Site Visit - Architect | Done | FALSE | 2025-01-15 | 2025-01-16 | 1 | 14 | 0 | Dark Blue | 1
SE11-04 | Initial Site Visit - Designer | Done | FALSE | 2025-01-15 | 2025-01-16 | 1 | 14 | 0 | Dark Blue | 1
SE11-05 | Send Architectural RFP | Done | FALSE | 2025-01-16 | 2025-01-17 | 1 | 15 | 0 | Dark Blue | 1
SE11-06 | Architectural Due Diligence & Proposal | Done | FALSE | 2025-01-17 | 2025-01-31 | 14 | 16 | 0 | Light Blue | 2
SE11-07 | Engineering Due Diligence & Proposal | Done | FALSE | 2025-01-17 | 2025-01-31 | 14 | 16 | 0 | Light Blue | 2
SE11-08 | Landscaping Due Diligence & Proposal | Done | FALSE | 2025-01-17 | 2025-01-31 | 14 | 16 | 0 | Light Blue | 2
SE11-09 | Hire Architect / Engineer | Done | FALSE | 2025-01-31 | 2025-02-14 | 14 | 30 | 0 | Light Blue | 2
SE11-10 | Architectual Drafting and Review | Done | FALSE | 2025-02-14 | 2025-03-16 | 30 | 44 | 16500 | Light Blue | 2
SE11-11 | Building Permit Application | Done | FALSE | 2025-03-16 | 2025-03-30 | 14 | 74 | 275 | Light Blue | 2
SE11-12 | Architectural Plan Revisions | Done | FALSE | 2025-03-16 | 2025-03-23 | 7 | 74 | 0 | Light Blue | 2
SE11-13 | Engineering Plan Revisions | Done | FALSE | 2025-03-16 | 2025-03-23 | 7 | 74 | 0 | Light Blue | 2
SE11-14 | Landscaping Plan Revisions | Done | FALSE | 2025-03-16 | 2025-03-23 | 7 | 74 | 0 | Light Blue | 2
SE11-15 | Send Contractor RFP | Done | FALSE | 2025-03-23 | 2025-03-24 | 1 | 81 | 0 | Light Blue | 2
SE11-16 | Planning Board Review - Site / Civil | Done | FALSE | 2025-03-24 | 2025-04-07 | 14 | 82 | 10797.2553 | Grey | 3
SE11-17 | Zoning Board Review | Done | FALSE | 2025-03-24 | 2025-04-07 | 14 | 82 | 5398.6277 | Grey | 3
SE11-18 | Architecture Board Review | Done | FALSE | 2025-04-07 | 2025-04-21 | 14 | 96 | 5398.6277 | Grey | 3
SE11-19 | Building Department Review | To Do | TRUE | 2025-04-21 | 2025-05-05 | 14 | 110 | 5398.6277 | Grey | 3
SE11-20 | Punchlist Value Engineer | To Do | TRUE | 2025-04-21 | 2025-05-05 | 14 | 110 | 0 | Purple | 0
SE11-21 | GC Due Diligence & Proposal | To Do | FALSE | 2025-04-21 | 2025-04-28 | 7 | 110 | 0 | Light Blue | 2
SE11-22 | Design Due Diligence & Proposal | To Do | FALSE | 2025-04-21 | 2025-04-28 | 7 | 110 | 0 | Light Blue | 2
SE11-23 | Review GC Proposals | To Do | FALSE | 2025-04-28 | 2025-05-05 | 7 | 117 | 0 | Light Blue | 2
SE11-24 | Review Design Proposals | To Do | FALSE | 2025-04-28 | 2025-05-05 | 7 | 117 | 0 | Light Blue | 2
SE11-25 | Site Visit (#2) - Contactor | To Do | FALSE | 2025-05-06 | 2025-05-07 | 1 | 125 | 0 | Dark Blue | 1
SE11-26 | Site Visit (#2) - Designer | To Do | FALSE | 2025-05-06 | 2025-05-07 | 1 | 125 | 0 | Dark Blue | 1
SE11-27 | Accept Proposals & Sign Contracts | To Do | FALSE | 2025-05-07 | 2025-05-08 | 1 | 126 | 104198.0791 | Dark Blue | 1
SE11-28 | Obtain Building Permits | To Do | FALSE | 2025-05-08 | 2025-05-09 | 1 | 127 | 165 | Grey | 3
SE11-29 | Order Kitchen Appliances | To Do | FALSE | 2025-05-09 | 2025-05-16 | 7 | 128 | 22875.6 | Cyan | 5
SE11-30 | Order Windows & Siding | To Do | FALSE | 2025-05-09 | 2025-05-16 | 7 | 128 | 41068.5 | Cyan | 5
SE11-31 | Order Cabinetry (Kitchen / Bath) | To Do | FALSE | 2025-05-09 | 2025-05-16 | 7 | 128 | 66000 | Cyan | 5
SE11-32 | Order Countertops & Tiling | To Do | FALSE | 2025-05-09 | 2025-05-16 | 7 | 128 | 5568.75 | Cyan | 5
SE11-33 | Order Above Grade Flooring | To Do | FALSE | 2025-05-09 | 2025-05-16 | 7 | 128 | 14419.35 | Cyan | 5
SE11-34 | Order Bathroom Vanities | To Do | FALSE | 2025-05-09 | 2025-05-16 | 7 | 128 | 8250 | Cyan | 5
SE11-35 | Order Hardware & Fixtures | To Do | FALSE | 2025-05-09 | 2025-05-16 | 7 | 128 | 5024.8 | Cyan | 5
SE11-36 | Order HVAC Unit | To Do | FALSE | 2025-05-09 | 2025-05-16 | 7 | 128 | 17644 | Cyan | 5
SE11-37 | Shut off of Utilities | To Do | FALSE | 2025-05-16 | 2025-05-17 | 1 | 135 | 6708.24 | Blue | 4
SE11-38 | Demolition of Existing Structure | To Do | FALSE | 2025-05-18 | 2025-06-01 | 14 | 137 | 47784 | Blue | 4
SE11-39 | Land Clearing & Site Grading | To Do | FALSE | 2025-05-18 | 2025-05-25 | 7 | 137 | 17248 | Blue | 4
SE11-40 | Excavation for Foundation & Utilities | To Do | FALSE | 2025-05-25 | 2025-06-01 | 7 | 144 | 19712 | Blue | 4
SE11-41 | Install OnSite Hospitalities | To Do | FALSE | 2025-06-01 | 2025-06-02 | 1 | 151 | 1276 | Blue | 4
SE11-42 | Install Drainage & Stormwater System | To Do | FALSE | 2025-06-01 | 2025-06-15 | 14 | 151 | 26400 | Blue | 4
SE11-43 | Form & Pour Foundation Footings | To Do | FALSE | 2025-06-01 | 2025-06-03 | 2 | 151 | 49500 | Blue | 4
SE11-44 | Foundation Inspection #1 | To Do | FALSE | 2025-06-03 | 2025-06-04 | 1 | 153 | 0 | Grey | 3
SE11-45 | Build Foundation Walls / Slab | To Do | FALSE | 2025-06-03 | 2025-06-10 | 7 | 153 | 34953.27 | Blue | 4
SE11-46 | Waterproof Foundation & Backfill | To Do | FALSE | 2025-06-10 | 2025-06-17 | 7 | 160 | 3960 | Blue | 4
SE11-47 | Foundation Utility Tie-In | To Do | FALSE | 2025-06-17 | 2025-06-24 | 7 | 167 | 2874.96 | Blue | 4
SE11-48 | Foundation Inspection #2 | To Do | FALSE | 2025-06-24 | 2025-06-25 | 1 | 174 | 0 | Grey | 3
SE11-49 | Civil Engineering Inspection | To Do | FALSE | 2025-06-25 | 2025-06-26 | 1 | 175 | 0 | Grey | 3
SE11-50 | Frame Floors & Subfloors | To Do | FALSE | 2025-06-25 | 2025-07-02 | 7 | 175 | 9462.2 | Blue | 4
SE11-51 | Frame Exterior & Interior Walls | To Do | FALSE | 2025-07-02 | 2025-07-09 | 7 | 182 | 19123.5 | Blue | 4
SE11-52 | Frame Roof & Install Sheating | To Do | FALSE | 2025-07-09 | 2025-07-16 | 7 | 189 | 70702.2 | Blue | 4
SE11-53 | Install Windows & Exterior Doors | To Do | FALSE | 2025-07-16 | 2025-07-23 | 7 | 196 | 924 | Blue | 4
SE11-54 | Framing Inspection | To Do | FALSE | 2025-07-24 | 2025-07-25 | 1 | 204 | 0 | Grey | 3
SE11-55 | Install Roof Shingles | To Do | FALSE | 2025-07-23 | 2025-07-30 | 7 | 203 | 7040 | Blue | 4
SE11-56 | Install Rough Plumbing | To Do | FALSE | 2025-07-30 | 2025-08-13 | 14 | 210 | 8580 | Blue | 4
SE11-57 | Install Rough Electrical | To Do | FALSE | 2025-08-13 | 2025-08-27 | 14 | 224 | 76340.99 | Blue | 4
SE11-58 | Plumbing & Electrical Inspection | To Do | FALSE | 2025-08-27 | 2025-08-28 | 1 | 238 | 0 | Grey | 3
SE11-59 | Install Rough HVAC Ductwork | To Do | FALSE | 2025-08-29 | 2025-09-12 | 14 | 240 | 440 | Blue | 4
SE11-60 | Install Exterior Siding & Insulation | To Do | FALSE | 2025-09-13 | 2025-09-20 | 7 | 255 | 18227 | Blue | 4
SE11-61 | Weatherproof Structure Inspection | To Do | FALSE | 2025-09-21 | 2025-09-22 | 1 | 263 | 0 | Grey | 3
SE11-62 | Install Decks, Patios, & Fences | To Do | FALSE | 2025-09-22 | 2025-10-06 | 14 | 264 | 115.5 | Blue | 4
SE11-63 | Install Interior Drywall | To Do | FALSE | 2025-09-22 | 2025-09-29 | 7 | 264 | 10406.1375 | Blue | 4
SE11-64 | Install Hardwood / Stone Floors | To Do | FALSE | 2025-09-29 | 2025-10-06 | 7 | 271 | 0 | Blue | 4
SE11-65 | Prime Walls & Ceilings (1st Coat) | To Do | FALSE | 2025-10-06 | 2025-10-08 | 2 | 278 | 9350 | Blue | 4
SE11-66 | Install Interior & Exterior Trim | To Do | FALSE | 2025-10-06 | 2025-10-13 | 7 | 278 | 28257.9 | Blue | 4
SE11-67 | Install Cabinetry (Kitchen & Bath) | To Do | FALSE | 2025-10-06 | 2025-10-13 | 7 | 278 | 0 | Blue | 4
SE11-68 | Install Countertops & Tiling | To Do | FALSE | 2025-10-06 | 2025-10-13 | 7 | 278 | 990 | Blue | 4
SE11-69 | Install Closet Shelving | To Do | FALSE | 2025-10-06 | 2025-10-13 | 7 | 278 | 11550 | Blue | 4
SE11-70 | Install Kitchen Appliances | To Do | FALSE | 2025-10-06 | 2025-10-13 | 7 | 278 | 2420 | Blue | 4
SE11-71 | Install Interior Hardware | To Do | FALSE | 2025-10-06 | 2025-10-13 | 7 | 278 | 431.64 | Blue | 4
SE11-72 | Install Plumbing Fixtures | To Do | FALSE | 2025-10-06 | 2025-10-13 | 7 | 278 | 4.455 | Blue | 4
SE11-73 | Install Electrical Fixtures | To Do | FALSE | 2025-10-06 | 2025-10-13 | 7 | 278 | 45827.1 | Blue | 4
SE11-74 | Install HVAC Units & Thermostats | To Do | FALSE | 2025-10-06 | 2025-10-13 | 7 | 278 | 99 | Blue | 4
SE11-75 | Paint Walls & Ceilings (2nd Coat) | To Do | FALSE | 2025-10-13 | 2025-10-27 | 14 | 285 | 10725 | Blue | 4
SE11-76 | Stain Hardwood Floors (1st Coat) | To Do | FALSE | 2025-10-27 | 2025-10-29 | 2 | 299 | 1004.3 | Blue | 4
SE11-77 | Stain Hardwood Floors (2nd Coat) | To Do | FALSE | 2025-10-29 | 2025-10-31 | 2 | 301 | 1004.3 | Blue | 4
SE11-78 | Install Flooring (Carpet & LVF) | To Do | FALSE | 2025-10-29 | 2025-10-31 | 2 | 301 | 4925.525 | Blue | 4
SE11-79 | Order Exterior Landscaping | To Do | FALSE | 2025-10-31 | 2025-11-01 | 1 | 303 | 87905.6475 | Cyan | 5
SE11-80 | Pour Driveway & Walkways | To Do | FALSE | 2025-11-01 | 2025-11-03 | 2 | 304 | 5009.4 | Blue | 4
SE11-81 | Install Exterior Landscaping | To Do | FALSE | 2025-11-01 | 2025-11-08 | 7 | 304 | 10071.2714 | Blue | 4
SE11-82 | Final Site Survey | To Do | FALSE | 2025-11-01 | 2025-11-02 | 1 | 304 | 1100 | Blue | 4
SE11-83 | Deck and Patio Inspection | To Do | FALSE | 2025-11-08 | 2025-11-09 | 1 | 311 | 0 | Grey | 3
SE11-84 | Interior & Exterior Touch-ups | To Do | FALSE | 2025-11-09 | 2025-11-11 | 2 | 312 | 0 | Blue | 4
SE11-85 | C of O Final Inspection | To Do | FALSE | 2025-11-11 | 2025-11-12 | 1 | 314 | 0 | Grey | 3
SE11-86 | Obtain Certificate of Occupancy | To Do | FALSE | 2025-11-12 | 2025-11-13 | 1 | 315 | 0 | Grey | 3
SE11-87 | Moving Services (1 Week) | To Do | FALSE | 2025-11-13 | 2025-11-14 | 1 | 316 | 0 | Blue | 4
SE11-88 | Final Touch-ups & Repairs | To Do | FALSE | 2025-11-14 | 2025-11-16 | 2 | 317 | 0 | Blue | 4
SE11-89 | Cleanup & Debris Removal | To Do | FALSE | 2025-11-16 | 2025-11-18 | 2 | 319 | 0 | Blue | 4
SE11-90 | Final Punchlist Walk-Through | To Do | FALSE | 2025-11-18 | 2025-11-19 | 1 | 321 | 49032.6931 | Purple | 0
Formulas:
End Date = [Start Date]+[Duration]
Start Date = [End Date, row above]
Start Date = [Start Date, row above]

## Pricing Info
`
11 Clinton Lane - Unit / Material Cost
Current Date: | 2025-03-23 |  |  |  | Total Project Duation (Hrs) |  | 0
Project Start: | 2025-01-01 |  |  |  | Expected Completion Date |  | 2025-11-19
Lot Size | 43560 |  |  |  | Construction Cost |  | 681647.2483 |  |  | Builder Grade (%) | 75%
Building SF | 4000 |  |  |  | GC Fee (%) | 15% | 104198.0791 |  |  | Market Grade (%) | 85%
# of Stories | 2 |  |  |  | Punchlist Fee (%) | 5% | 34732.6931 |  |  | Punchlist Grade (%) | 100%
Above Grade SF | 3400 |  |  |  | Total Project Cost |  | 820578.0205 |  |  | Design Grade (%) | 115%
Below Grade SF | 600 |  |  |  | $ per SF Cost |  | 205.1445 |  |  | Luxuary Grade (%) | 125%
Unit / Service Desciption | Unit Cost (1) | % Market Grade | Unit Cost + Grade | Total Units / SF | Labor Rate (Hr) | Expected Hours | Instillation Cost | Total Unit Cost | Waste (10.00%) | Final Unit Cost | Initiative Key
Aluminum Sheathing | 10 | 100% | 10 | 400 | 0 | 0 | 0 | 4000 | 400 | 4400 | SE11-52
Appliances (36" Range) | 5759.2 | 100% | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-29
Appliances (48” Range) | 9279.2 | 100% | 11500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-29
Appliances (60" Range) | 12799.2 | 100% | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-29
Appliances (Dishwasher) | 1119.2 | 100% | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-29
Appliances (30" Oven) | 3759.2 | 100% | 3759.2 | 1 | 0 | 0 | 0 | 3759.2 | 375.92 | 4135.12 | SE11-29
Appliances (30" Oven x2) | 5919.2 | 100% | 5919.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-29
Appliances (Microwave) | 919.2 | 100% | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-29
Appliances (Range, Electic) | 2399.2 | 100% | 2399.2 | 1 | 0 | 0 | 0 | 2399.2 | 239.92 | 2639.12 | SE11-29
Appliances (Range, Gas) | 1919.2 | 100% | 1919.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-29
Appliances (Range, Induction) | 3199.2 | 100% | 3199.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-29
Appliances (Freezer) | 6799.2 | 100% | 6799.2 | 1 | 0 | 0 | 0 | 6799.2 | 679.92 | 7479.12 | SE11-29
Appliances (Fridge) | 6799.2 | 100% | 6799.2 | 1 | 0 | 0 | 0 | 6799.2 | 679.92 | 7479.12 | SE11-29
Appliances (Fridge / Freezer) | 12799.2 | 100% | 12799.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-29
Appliances (Fridge / Mini) | 1039.2 | 100% | 1039.2 | 1 | 0 | 0 | 0 | 1039.2 | 103.92 | 1143.12 | SE11-29
Appliances (Warming Drawer) | 1439.2 | 100% | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-29
Approvals (Architectual) | 4907.8433 | 100% | 4907.8433 | 1 | 0 | 0 | 0 | 4907.8433 | 490.7843 | 5398.6277 | SE11-18
Approvals (Building Permits) | 250 | 100% | 250 | 1 | 0 | 0 | 0 | 250 | 25 | 275 | SE11-11
Approvals (Engineering) | 4907.8433 | 100% | 4907.8433 | 1 | 0 | 0 | 0 | 4907.8433 | 490.7843 | 5398.6277 | SE11-19
Approvals (Landscaping) | 4907.8433 | 100% | 4907.8433 | 1 | 0 | 0 | 0 | 4907.8433 | 490.7843 | 5398.6277 | SE11-16
Approvals (Zoning) | 4907.8433 | 100% | 4907.8433 | 1 | 0 | 0 | 0 | 4907.8433 | 490.7843 | 5398.6277 | SE11-17
Approvals (Site-Plan) | 4907.8433 | 100% | 4907.8433 | 1 | 0 | 0 | 0 | 4907.8433 | 490.7843 | 5398.6277 | SE11-16
Cabinetry (Kitchen / Bath) | 1200 | 100% | 1200 | 50 | 0 | 0 | 0 | 60000 | 6000 | 66000 | SE11-31
Countertops (Quartz) | 45 | 100% | 45 | 112.5 | 0 | 0 | 0 | 5062.5 | 506.25 | 5568.75 | SE11-32
Countertops (Grantie) | 35 | 100% | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-32
Copper (Gutters) | 17.5 | 100% | 17.5 | 400 | 0 | 0 | 0 | 7000 | 700 | 7700 | SE11-52
Copper (Wiring) | 6 | 100% | 6 | 10000 | 0 | 0 | 0 | 60000 | 6000 | 66000 | SE11-57
Cultec (Storm Water) | 7 | 100% | 6 | 4000 | 0 | 0 | 0 | 24000 | 2400 | 26400 | SE11-42
Deck (Hardwood) | 25 | 100% | 25 | 1 | 0 | 0 | 0 | 25 | 2.5 | 27.5 | SE11-62
Deck (Vinyl) | 18 | 100% | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-62
Driveway (Asphault) | 6 | 100% | 6 | 600 | 0 | 0 | 0 | 3600 | 360 | 3960 | SE11-80
Driveway (Crushed Gravel) | 3 | 100% | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-80
Driveway (Pavers) | 12 | 100% | 22 | 27 | 0 | 0 | 0 | 594 | 59.4 | 653.4 | SE11-80
Electrical (Circuit Breaker) | 400 | 100% | 400 | 1 | 0 | 0 | 0 | 400 | 40 | 440 | SE11-57
Electrical (Generator) | 5000 | 100% | 5000 | 1 | 0 | 0 | 0 | 5000 | 500 | 5500 | SE11-73
Flooring (Carpet) | 4 | 100% | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-78
Flooring (Hardwood) | 8 | 100% | 9.5 | 3 | 0 | 0 | 0 | 28.5 | 2.85 | 31.35 | SE11-33
Flooring (LVF) | 6 | 100% | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-78
Flooring (Wood Stain) | 1 | 100% | 1 | 3 | 0 | 0 | 0 | 3 | 0.3 | 3.3 | SE11-76
Flooring (Wood Stain #2) | 1 | 100% | 1 | 3 | 0 | 0 | 0 | 3 | 0.3 | 3.3 | SE11-77
Flooring (Stone) | 15 | 100% | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-33
Flooring (Vinyl) | 3 | 100% | 4.25 | 3 | 0 | 0 | 0 | 12.75 | 1.275 | 14.025 | SE11-78
Foundations (Concrete) | 12 | 100% | 12 | 3000 | 0 | 0 | 0 | 36000 | 3600 | 39600 | SE11-43
Foundations (Steel) | 15 | 100% | 15 | 600 | 0 | 0 | 0 | 9000 | 900 | 9900 | SE11-43
Hardware (Blinds) | 6 | 100% | 6 | 6 | 0 | 0 | 0 | 36 | 3.6 | 39.6 | SE11-35
Hardware (Door Knobs) | 20 | 100% | 20 | 20 | 0 | 0 | 0 | 400 | 40 | 440 | SE11-35
Hardware (Doors) | 150 | 100% | 150 | 20 | 0 | 0 | 0 | 3000 | 300 | 3300 | SE11-30
Hardware (Shades) | 8 | 100% | 8 | 14 | 0 | 0 | 0 | 112 | 11.2 | 123.2 | SE11-35
Hardware (Windows) | 600 | 100% | 600 | 40 | 0 | 0 | 0 | 24000 | 2400 | 26400 | SE11-30
HVAC (Central AC) | 6 | 100% | 6 | 40 | 0 | 0 | 0 | 240 | 24 | 264 | SE11-36
HVAC (Heated Floors) | 12 | 100% | 12 | 40 | 0 | 0 | 0 | 480 | 48 | 528 | SE11-36
HVAC (Split System) | 8 | 100% | 8 | 40 | 0 | 0 | 0 | 320 | 32 | 352 | SE11-36
HVAC (Duct Wok) | 15 | 100% | 15 | 1000 | 0 | 0 | 0 | 15000 | 1500 | 16500 | SE11-36
Insulation (Foam) | 2.5 | 100% | 2.5 | 5000 | 0 | 0 | 0 | 12500 | 1250 | 13750 | SE11-60
Insulation (Fiber Glass) | 1.5 | 100% | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-60
Landscaping (Dirt) | 0.5 | 100% | 0.5 | 43560 | 0 | 0 | 0 | 21780 | 2178 | 23958 | SE11-38
Landscaping (Grass Seed) | 0.01 | 100% | 0.01 | 43560 | 0 | 0 | 0 | 435.6 | 43.56 | 479.16 | SE11-79
Landscaping (Grass Sod) | 0.35 | 100% | 1.75 | 80 | 0 | 0 | 0 | 140 | 14 | 154 | SE11-79
Landscaping (Mailbox) | 250 | 100% | 250 | 1 | 0 | 0 | 0 | 250 | 25 | 275 | SE11-79
Landscaping (Rock) | 1 | 100% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-79
Landscaping (Shade Trees) | 1000 | 100% | 1000 | 76.23 | 0 | 0 | 0 | 76230 | 7623 | 83853 | SE11-79
Landscaping (Shrubs) | 50 | 100% | 50 | 57.1725 | 0 | 0 | 0 | 2858.625 | 285.8625 | 3144.4875 | SE11-79
Light Switches | 30 | 100% | 30 | 54 | 0 | 0 | 0 | 1620 | 162 | 1782 | SE11-35
Lighting Fixtures | 150 | 100% | 150 | 16 | 0 | 0 | 0 | 2400 | 240 | 2640 | SE11-35
Machinery (Light) | 750 | 100% | 750 | 2 | 0 | 0 | 0 | 1500 | 150 | 1650 | SE11-38
Municipal Inspection | 0 | 100% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-44
Paint (2nd Coat) | 1.5 | 100% | 1.5 | 5000 | 0 | 0 | 0 | 7500 | 750 | 8250 | SE11-75
Paint (1st Coat / Primer) | 1.25 | 100% | 1.25 | 5000 | 0 | 0 | 0 | 6250 | 625 | 6875 | SE11-65
Patio (Blue Stone) | 30 | 100% | 30 | 436 | 0 | 0 | 0 | 13080 | 1308 | 14388 | SE11-33
Patio (Brick) | 18 | 100% | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-33
Patio (Gravel) | 22 | 100% | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-33
Plywood / Subboard | 1.8 | 100% | 1.8 | 3740 | 0 | 0 | 0 | 6732 | 673.2 | 7405.2 | SE11-50
Project Fee (Architect) | 0 | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-27
Project Fee (Designer) | 0 | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-27
Project Fee (GC) | 631503.51 | 15% | 94725.5265 | 1 | 0 | 0 | 0 | 94725.5265 | 9472.5526 | 104198.0791 | SE11-27
Project Fee (Punchlist) | 631503.51 | 5% | 31575.1755 | 1 | 0 | 0 | 0 | 31575.1755 | 3157.5176 | 34732.6931 | SE11-90
PVC Pipes | 1.5 | 100% | 1.5 | 4000 | 0 | 0 | 0 | 6000 | 600 | 6600 | SE11-56
Recessed Lighting | 90 | 100% | 90 | 400 | 0 | 0 | 0 | 36000 | 3600 | 39600 | SE11-73
Sealant (Caulking) | 0.75 | 100% | 0.75 | 1000 | 0 | 0 | 0 | 750 | 75 | 825 | SE11-60
Site Survey (1st Visit) | 0 | 100% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-02
Site Survey (C of O) | 0 | 100% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-82
Sheetrock | 1.25 | 100% | 1.25 | 4400 | 0 | 0 | 0 | 5500 | 550 | 6050 | SE11-63
Shelving (Closets) | 10 | 100% | 10 | 1000 | 0 | 0 | 0 | 10000 | 1000 | 11000 | SE11-69
Shingels (Asphalt) | 4 | 100% | 4 | 12800 | 0 | 0 | 0 | 51200 | 5120 | 56320 | SE11-52
Shingels (Metal) | 10 | 100% | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-52
Shingels (Slate) | 20 | 100% | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-52
Shingles (Wood) | 12 | 100% | 12 | 1 | 0 | 0 | 0 | 12 | 1.2 | 13.2 | SE11-52
Siding (Brick) | 15 | 100% | 15 | 1 | 0 | 0 | 0 | 15 | 1.5 | 16.5 | SE11-30
Siding (Hardie Board) | 9 | 100% | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-30
Siding (Shutters) | 2.5 | 100% | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-30
Siding (Stone) | 20 | 100% | 20 | 16 | 0 | 0 | 0 | 320 | 32 | 352 | SE11-30
Siding (Wood) | 10 | 100% | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-30
Support Beams (Steel) | 400 | 100% | 1200 | 1 | 0 | 0 | 0 | 1200 | 120 | 1320 | SE11-45
Support Beams (Wood) | 10 | 100% | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-45
Trim (Baseboard Molding) | 3 | 100% | 3 | 2667 | 0 | 0 | 0 | 8001 | 800.1 | 8801.1 | SE11-66
Trim (Crown Molding) | 4 | 100% | 4 | 2667 | 0 | 0 | 0 | 10668 | 1066.8 | 11734.8 | SE11-66
Trim (2" x 4") | 5 | 100% | 5 | 2667 | 0 | 0 | 0 | 13335 | 1333.5 | 14668.5 | SE11-51
Trim (Finishes) | 2.5 | 100% | 2.5 | 400.05 | 0 | 0 | 0 | 1000.125 | 100.0125 | 1100.1375 | SE11-63
Temporary Utilities | 500 | 100% | 500 | 2 | 0 | 0 | 0 | 1000 | 100 | 1100 | SE11-41
Tyveck / Waterproofing | 1.25 | 100% | 1.25 | 8000 | 0 | 0 | 0 | 10000 | 1000 | 11000 | SE11-30
Vanity (Bathtub) | 1200 | 100% | 1200 | 1 | 0 | 0 | 0 | 1200 | 120 | 1320 | SE11-34
Vanity (Bathtub / Shower) | 1500 | 100% | 1500 | 1 | 0 | 0 | 0 | 1500 | 150 | 1650 | SE11-34
Vanity (Bidet) | 600 | 100% | 600 | 1 | 0 | 0 | 0 | 600 | 60 | 660 | SE11-34
Vanity (Double Sink) | 1800 | 100% | 1800 | 1 | 0 | 0 | 0 | 1800 | 180 | 1980 | SE11-34
Vanity (Shower) | 5000 | 100% | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-34
Vanity (Sink) | 800 | 100% | 800 | 3 | 0 | 0 | 0 | 2400 | 240 | 2640 | SE11-34
820578.0205
11 Clinton Lane - Instillation Cost
Current Date: | 2025-03-23 |  |  |  | Total Project Duation (Hrs) |  | 1192.144
Project Start: | 2025-01-01 |  |  |  | Expected Completion Date |  | 0
Lot Size | 43560 |  |  |  | Instillation Cost |  | 168063.2264 |  |  | Hourly - Architectual | 250
Building SF | 4000 |  |  |  | Professional Hourly | 250 | 42583.2 |  |  | Hourly - Design | 150
# of Stories | 2 |  |  |  | Punchlist Hourly | 100 | 5500 |  |  | Hourly - GC | 150
Above Grade SF | 3400 |  |  |  | Total Instillation Cost |  | 216146.4264 |  |  | Hourly - Punchlist | 100
Below Grade SF | 600 |  |  |  | $ per SF Cost |  | 54.0366 |  |  | AVG Hourly Rate | 181.309
Unit / Service Desciption | Unit Cost (1) | % Market Grade | Unit Cost + Grade | Total Units / SF | Labor Rate (Hr) | Expected Hours | Instillation Cost | Total Unit Cost | Waste (10.00%) | Final Unit Cost | Initiative Key
Instillation - Aluminum Sheathing | 0 | 0% | 0 | 400 | 85 | 4 | 340 | 0 | 34 | 344 | SE11-52
Instillation - Appliances (36" Range) | 0 | 0% | 0 | 1 | 100 | 2 | 200 | 0 | 20 | 220 | SE11-70
Instillation - Appliances (48” Range) | 0 | 0% | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | SE11-70
Instillation - Appliances (60" Range) | 0 | 0% | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | SE11-70
Instillation - Appliances (Dishwasher) | 0 | 0% | 0 | 1 | 100 | 2 | 200 | 0 | 20 | 220 | SE11-70
Instillation - Appliances (30" Oven) | 0 | 0% | 0 | 1 | 100 | 2 | 200 | 0 | 20 | 220 | SE11-70
Instillation - Appliances (30" Oven x2) | 0 | 0% | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | SE11-70
Instillation - Appliances (Microwave) | 0 | 0% | 0 | 1 | 100 | 2 | 200 | 0 | 20 | 220 | SE11-70
Instillation - Appliances (Range, Electic) | 0 | 0% | 0 | 1 | 100 | 2 | 200 | 0 | 20 | 220 | SE11-70
Instillation - Appliances (Range, Gas) | 0 | 0% | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | SE11-70
Instillation - Appliances (Range, Induction) | 0 | 0% | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | SE11-70
Instillation - Appliances (Freezer) | 0 | 0% | 0 | 1 | 100 | 2 | 200 | 0 | 20 | 220 | SE11-70
Instillation - Appliances (Fridge) | 0 | 0% | 0 | 1 | 100 | 2 | 200 | 0 | 20 | 220 | SE11-70
Instillation - Appliances (Fridge / Freezer) | 0 | 0% | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | SE11-70
Instillation - Appliances (Fridge / Mini) | 0 | 0% | 0 | 1 | 100 | 2 | 200 | 0 | 20 | 220 | SE11-70
Instillation - Appliances (Warming Drawer) | 0 | 0% | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | SE11-70
Instillation - Cabinetry (Kitchen) | 0 | 0% | 0 | 30 | 100 | 6 | 600 | 0 | 60 | 660 | SE11-70
Instillation - Copper (Gutters) | 0 | 0% | 0 | 400 | 87.5 | 20 | 1750 | 0 | 175 | 1925 | SE11-52
Instillation - Copper (Wiring) | 0 | 0% | 0 | 10000 | 90 | 100 | 9000 | 0 | 900 | 9900 | SE11-57
Instillation - Counter Tops | 0 | 0% | 0 | 5 | 90 | 10 | 900 | 0 | 90 | 990 | SE11-68
Instillation - Deck (Hardwood) | 0 | 0% | 0 | 1 | 80 | 1 | 80 | 0 | 8 | 88 | SE11-62
Instillation - Deck (Vinyl) | 0 | 0% | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | SE11-62
Instillation - Driveway (Asphault) | 0 | 0% | 0 | 600 | 60 | 6 | 360 | 0 | 36 | 396 | SE11-80
Instillation - Driveway (Crushed Gravel) | 0 | 0% | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | SE11-80
Instillation - Driveway (Pavers) | 0 | 0% | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | SE11-80
Instillation - Electrical (Circuit Breaker) | 0 | 0% | 0 | 1 | 90 | 0.01 | 0.9 | 0 | 0.09 | 0.99 | SE11-57
Instillation - Electrical (Generator) | 0 | 0% | 0 | 1 | 100 | 0.01 | 1 | 0 | 0.1 | 1.1 | SE11-73
Instillation - Flooring (Carpet) | 0 | 0% | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | SE11-78
Instillation - Flooring (Hardwood) | 0 | 0% | 0 | 3400 | 65 | 68 | 4420 | 0 | 442 | 4862 | SE11-78
Instillation - Flooring (LVF) | 0 | 0% | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | SE11-64
Instillation - Flooring (Stain #1) | 0 | 0% | 0 | 3400 | 65 | 14 | 910 | 0 | 91 | 1001 | SE11-76
Instillation - Flooring (Stain #2) | 0 | 0% | 0 | 3400 | 65 | 14 | 910 | 0 | 91 | 1001 | SE11-77
Instillation - Flooring (Stone) | 0 | 0% | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | SE11-64
Instillation - Flooring (Vinyl) | 0 | 0% | 0 | 1 | 45 | 1 | 45 | 0 | 4.5 | 49.5 | SE11-78
Instillation - Foundations (Concrete) | 0 | 0% | 0 | 3000 | 70 | 30 | 2100 | 0 | 210 | 2310 | SE11-45
Instillation - Foundations (Steel) | 0 | 0% | 0 | 600 | 75 | 6 | 450 | 0 | 45 | 495 | SE11-45
Instillation - Hardware (Blinds) | 0 | 0% | 0 | 6 | 40 | 0.06 | 2.4 | 0 | 0.24 | 2.64 | SE11-71
Instillation - Hardware (Door Knobs) | 0 | 0% | 0 | 20 | 50 | 0.2 | 10 | 0 | 1 | 11 | SE11-71
Instillation - Hardware (Doors) | 0 | 0% | 0 | 20 | 65 | 4 | 260 | 0 | 26 | 286 | SE11-71
Instillation - Hardware (Shades) | 0 | 0% | 0 | 14 | 40 | 3 | 120 | 0 | 12 | 132 | SE11-71
Instillation - Hardware (Widows) | 0 | 0% | 0 | 40 | 60 | 14 | 840 | 0 | 84 | 924 | SE11-53
Instillation - HVAC (Central AC) | 0 | 0% | 0 | 40 | 75 | 0.4 | 30 | 0 | 3 | 33 | SE11-74
Instillation - HVAC (Heated Floors) | 0 | 0% | 0 | 40 | 80 | 0.4 | 32 | 0 | 3.2 | 35.2 | SE11-74
Instillation - HVAC (Split System) | 0 | 0% | 0 | 40 | 70 | 0.4 | 28 | 0 | 2.8 | 30.8 | SE11-74
Instillation - HVAC (Duct Wok) | 0 | 0% | 0 | 1000 | 40 | 10 | 400 | 0 | 40 | 440 | SE11-59
Instillation - Insulation (Foam) | 0 | 0% | 0 | 5000 | 60 | 50 | 3000 | 0 | 300 | 3300 | SE11-60
Instillation - Insulation (Fiber Glass) | 0 | 0% | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | SE11-60
Instillation - Landscaping (Dirt) | 0 | 0% | 0 | 43560 | 50 | 87.12 | 4356 | 0 | 435.6 | 4791.6 | SE11-81
Instillation - Landscaping (Grass Seed) | 0 | 0% | 0 | 43560 | 50 | 87.12 | 4356 | 0 | 435.6 | 4791.6 | SE11-81
Instillation - Landscaping (Grass Sod) | 0 | 0% | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | SE11-81
Instillation - Landscaping (Mailbox) | 0 | 0% | 0 | 1 | 50 | 1 | 50 | 0 | 5 | 55 | SE11-81
Instillation - Landscaping (Rock) | 0 | 0% | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | SE11-81
Instillation - Landscaping (Shade Trees) | 0 | 0% | 0 | 76.23 | 50 | 0.7623 | 38.115 | 0 | 3.8115 | 41.9265 | SE11-81
Instillation - Landscaping (Shrubs) | 0 | 0% | 0 | 57.1725 | 50 | 0.57173 | 28.5863 | 0 | 2.8586 | 31.4449 | SE11-81
Instillation - Light Switches | 0 | 0% | 0 | 54 | 50 | 3 | 150 | 0 | 15 | 165 | SE11-73
Instillation - Lighting Fixtures | 0 | 0% | 0 | 16 | 70 | 2 | 140 | 0 | 14 | 154 | SE11-73
Instillation - Machinery | 0 | 0% | 0 | 1 | 70 | 1 | 70 | 0 | 7 | 77 | SE11-73
Instillation - Paint (2nd Coat) | 0 | 0% | 0 | 5000 | 45 | 50 | 2250 | 0 | 225 | 2475 | SE11-75
Instillation - Paint (1st Coat / Primer) | 0 | 0% | 0 | 5000 | 45 | 50 | 2250 | 0 | 225 | 2475 | SE11-65
Instillation - Patio (Blue Stone) | 0 | 0% | 0 | 436 | 75 | 4.36 | 327 | 0 | 32.7 | 359.7 | SE11-81
Instillation - Patio (Brick) | 0 | 0% | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | SE11-81
Instillation - Patio (Gravel) | 0 | 0% | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | SE11-81
Instillation - Plywood / Subboard | 0 | 0% | 0 | 3740 | 50 | 37.4 | 1870 | 0 | 187 | 2057 | SE11-50
Instillation - PVC Pipes | 0 | 0% | 0 | 4000 | 45 | 40 | 1800 | 0 | 180 | 1980 | SE11-56
Instillation - Recessed Lighting | 0 | 0% | 0 | 400 | 75 | 4 | 300 | 0 | 30 | 330 | SE11-73
Instillation - Sealant (Caulking) | 0 | 0% | 0 | 1000 | 40 | 4 | 160 | 0 | 16 | 176 | SE11-60
Instillation - Sheetrock | 0 | 0% | 0 | 4400 | 55 | 44 | 2420 | 0 | 242 | 2662 | SE11-63
Instillation - Shelving (Closets) | 0 | 0% | 0 | 1000 | 50 | 10 | 500 | 0 | 50 | 550 | SE11-69
Instillation - Shingels (Asphalt) | 0 | 0% | 0 | 12800 | 50 | 128 | 6400 | 0 | 640 | 7040 | SE11-55
Instillation - Shinges (Metal) | 0 | 0% | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | SE11-55
Instillation - Shinges (Slate) | 0 | 0% | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | SE11-55
Instillation - Shingles (Wood) | 0 | 0% | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | SE11-55
Instillation - Siding (Brick) | 0 | 0% | 0 | 1 | 75 | 1 | 75 | 0 | 7.5 | 82.5 | SE11-60
Instillation - Siding (Hardie Board) | 0 | 0% | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | SE11-60
Instillation - Siding (Shutters) | 0 | 0% | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | SE11-60
Instillation - Siding (Stone) | 0 | 0% | 0 | 16 | 85 | 1 | 85 | 0 | 8.5 | 93.5 | SE11-60
Instillation - Siding (Wood) | 0 | 0% | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | SE11-60
Instillation - Support Beams (Steel) | 0 | 0% | 0 | 1 | 2500 | 2.25 | 5625 | 0 | 562.5 | 6187.5 | SE11-45
Instillation - Support Beams (Wood) | 0 | 0% | 0 | 1 | 70 | 0.01 | 0.7 | 0 | 0.07 | 0.77 | SE11-45
Instillation - Trim (Baseboard Molding) | 0 | 0% | 0 | 2667 | 60 | 54 | 3240 | 0 | 324 | 3564 | SE11-66
Instillation - Trim (Crown Molding) | 0 | 0% | 0 | 2667 | 70 | 54 | 3780 | 0 | 378 | 4158 | SE11-66
Instillation - Trim (2" x 4") | 0 | 0% | 0 | 2667 | 75 | 54 | 4050 | 0 | 405 | 4455 | SE11-51
Instillation - Trim (Finishes) | 0 | 0% | 0 | 400.05 | 60 | 9 | 540 | 0 | 54 | 594 | SE11-63
Instillation - Temporary Utilities | 0 | 0% | 0 | 2 | 40 | 4 | 160 | 0 | 16 | 176 | SE11-41
Instillation - Tyveck / Waterproofing | 0 | 0% | 0 | 8000 | 45 | 80 | 3600 | 0 | 360 | 3960 | SE11-46
Instillation - Vanity (Bathtub) | 0 | 0% | 0 | 1 | 60 | 0.01 | 0.6 | 0 | 0.06 | 0.66 | SE11-72
Instillation - Vanity (Bathtub/Shower) | 0 | 0% | 0 | 1 | 70 | 0.01 | 0.7 | 0 | 0.07 | 0.77 | SE11-72
Instillation - Vanity (Bidet) | 0 | 0% | 0 | 1 | 60 | 0.01 | 0.6 | 0 | 0.06 | 0.66 | SE11-72
Instillation - Vanity (Double Sink) | 0 | 0% | 0 | 1 | 65 | 0.01 | 0.65 | 0 | 0.065 | 0.715 | SE11-72
Instillation - Vanity (Shower) | 0 | 0% | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | SE11-72
Instillation - Vanity (Sink) | 0 | 0% | 0 | 3 | 50 | 0.03 | 1.5 | 0 | 0.15 | 1.65 | SE11-72
Hourly - Building Permits | 0 | 0% | 0 | 1 | 150 | 1 | 150 | 0 | 15 | 165 | SE11-28
Hourly - Clearing & Site Grading | 0 | 0% | 0 | 10890 | 35 | 448 | 15680 | 0 | 1568 | 17248 | SE11-39
Hourly - Demolition | 0 | 0% | 0 | 800 | 45 | 448 | 20160 | 0 | 2016 | 22176 | SE11-38
Hourly - Excavation | 0 | 0% | 0 | 1000 | 40 | 448 | 17920 | 0 | 1792 | 19712 | SE11-40
Hourly - Form & Pour (Concrete) | 0 | 0% | 0 | 1000 | 50 | 448 | 22400 | 0 | 2240 | 24640 | SE11-45
Hourly - Project Fee (Architect) | 0 | 0% | 0 | 1 | 250 | 60 | 15000 | 0 | 1500 | 16500 | SE11-10
Hourly - Project Fee (Designer) | 0 | 0% | 0 | 1 | 100 | 100 | 10000 | 0 | 1000 | 11000 | SE11-90
Hourly - Project Fee (GC) | 0 | 0% | 0 | 0 | 150 | 20 | 3000 | 0 | 300 | 3300 | SE11-90
Hourly - Project Fee (Punchlist) | 0 | 0% | 0 | 0 | 100 | 50 | 5000 | 0 | 500 | 5500 | SE11-01
Hourly - Site Survey (1st Visit) | 0 | 0% | 0 | 1 | 250 | 4 | 1000 | 0 | 100 | 1100 | SE11-02
Hourly - Site Survey (C of O) | 0 | 0% | 0 | 1 | 250 | 4 | 1000 | 0 | 100 | 1100 | SE11-82
Hourly - Utilites (Con Edison) | 0 | 0% | 0 | 1 | 400 | 15.246 | 6098.4 | 0 | 609.84 | 6708.24 | SE11-37
Hourly - Utilites (Tie-In) | 0 | 0% | 0 | 1 | 400 | 6.534 | 2613.6 | 0 | 261.36 | 2874.96 | SE11-47
216146.4264
11 Clinton Lane - Total Project Cost
Total Project Cost | 820578.0205 |  |  |  | Professional Fees | 14.16% | 146781.2791 |  |  | Start Date | 2025-01-01
Total Instillation Cost | 216146.4264 |  |  |  | Punchlist Fees | 3.881% | 40232.6931 |  |  | End Date | 2025-11-19
Total Project Cost | 1036724.4469 |  |  |  | Total Additional Fees |  | 187013.9722 |  |  | Total Hours | 1192.144

## Color Code
Code | Color
0 | Purple
1 | Dark Blue
2 | Light Blue
3 | Grey
4 | Blue
5 | Cyan